## ①表紙
表紙
概算見積書 プロジェクト名：Knowledge & Assistance System バージョン：1.0 2025.10.30

## ③運用コストの見積もり
社内チャットボット向けAWSサービス（10～20名程度のチーム向け）
| （高速、最安コスト） | （性能とコストのバランス） | （マルチモーダルモデル、高性能）
| Claude 3 Haiku | Claude 4 Sonnet | gpt-oss-120b
Amazon Bedrock | $0.88 ~ $3.52 | $10.56 ~ $42.24 | $0.52 ~ $2.09
Amazon OpenSearch | 32 | 32 | 32
AWS Lambda | $0.00 - $5.00 | $0.00 - $5.00 | $0.00 - $5.00
Amazon S3 | $1.00 | $1.00 | $1.00
Amplify | $0.00 - $5.00 | $0.00 - $5.00 | $0.00 - $5.00
RDS db.t3.micro (optional) | $17.30 | $17.30 | $17.30
Route 53 - Public hosted zone per month | $0.5 | $0.5 | $0.5
IaC | $0.0 | $0.0 | $0.0
CI/CD + Build | $5.00 - $10.00 | $5.00 - $10.00 | $5.00 - $10.00
VPC/network (data transfer) | $10.0 | $10.0 | $10.0
その他のサービス（API Gateway, DynamoDB (cho agents), EventBridge） | $1.00 - $5.00 | $1.00 - $5.00 | $1.00 - $5.00
合計（月額） | $67.68 - $89.32 | $77.36 - $128.04 | $67.32 - $87.89
Amazon Bedrockの利用想定（10～20名程度のチーム向け）
* 一般情報
リージョン | ap-northeast-1 (Tokyo)
モード | On-Demand and Batch
1回のインタラクションあたりのトークン数： | - Input | 100 | tokens
| - Output | 300 | tokens
1回のインタラクションあたりのトークン数： | - Min | 10 | 人
| - Max | 20 | 人
1人あたりの1日の平均質問数 | - Min | 10 | 質問/日
| - Max | 20 | 質問/日
* 10人、月22営業日と仮定：
1日あたりのインタラクション数： | - Min | 100 | インタラクション/日
| - Max | 200 | インタラクション/日
1ヶ月あたりのインタラクション数: | - Min | 2200 | インタラクション/月
| - Max | 4400 | インタラクション/月
* 1ヶ月あたりの入出力トークン量
Min (1人あたり1日10質問) | - Input tokens | 220000 | tokens
| - Output tokens | 660000 | tokens
| - 合計 | 880000 | tokens
Max (1人あたり1日20質問): | - Input tokens | 440000 | tokens
| - Output tokens | 1320000 | tokens
| - 合計 | 1760000 | tokens
* 20人、月22営業日と仮定：
1日あたりのインタラクション数： | - Min | 200 | インタラクション/日
| - Max | 400 | インタラクション/日
1ヶ月あたりのインタラクション数： | - Min | 4400 | インタラクション/日
| - Max | 8800 | インタラクション/日
* 1ヶ月あたりの入出力トークン量：
Min (1人あたり1日10質問) | - Input tokens | 440000 | tokens
| - Output tokens | 1320000 | tokens
| - 合計 | 1760000 | tokens
Max (1人あたり1日20質問): | - Input tokens | 880000 | tokens
| - Output tokens | 2640000 | tokens
| - 合計 | 3520000 | tokens

## ④見積り工数
④見積り工数
【見 積 工 数】
積算した開発工数は、以下の表の通りです。
# | 工程 | 工数(MD) | 工数(MM) | 備考
1 | プロジェクト準備/ 開発環境の構築 | 10 | 0.5 | プロジェクト計画 開発環境（個人）,サーバ、テスト機準備
2 | 仕様確認（スタディ） アプリケーション方式設計 | 10 | 0.5 | 仕様確認、Q&A実施 アプリケーション処理方式の検討
3 | 詳細設計 (プログラム設計・DB設計) | 23.125 | 1.2 | 「⑤工数明細」 参照
4 | コーディング〜単体テスト | 138.75 | 6.9
5 | 結合テスト | 69.375 | 3.5
6 | 受入テスト対応 | 20 | 1
7 | デプロイ手順書・リリースノート 成果物確認 | 3 | 0.2
合計 |  | 274.25 | 13.8 | ※1~2人月バッファを確保頂ければと思います。 プロジェクトが順調にすすめば使用することはありませんが、必要時に備えていただけると助かります。
【要員山積みと概算費用 について】
# | 期間 | 参加人数 (人) | 工数 （人月） | 備考
1 | 2025年11月01日~ 11月30日 | 5 | 5
2 | 2025年12月01日~ 12月31日 | 5 | 5
3 | 2026年1月01日~ 1月16日 | 5 | 5
合計 |  | 15 | 15

## ⑤工数明細
[9 empty] | 難易度 | 1〜5
機能一覧 | [8 empty] | 基準 | 250 |  | 積算工数
生産性
# | エピック | ユーザーストーリーID | ペルソナ（誰？） 〜として | アクション（何？） 〜をしたい | 価値（なぜ？） 〜ができるように | 優先度 | スプリント |  |  |  |  | 工数(人日) | [6 empty] | 1.2
[8 empty] | 難易度 | 補正値 | 規模(step) | Memo | 詳細設計 | コーディング〜単体テスト | 結合テスト | 合計 | 備考 | CDD | 12000 | 12
1 | チャットボット管理 | US001 | 管理者 | チャットボット一覧の管理 | チャットボットの追加・編集・削除が可能。 以下のパラメータをカスタマイズ可能。 ・使用LLMモデル ・システムプロンプト | Must | 1 | 4 |  | 1000 |  | 1.6667 | 10 | 5 | 16.6667 |  | C-UT | 2000 | 2
2 | チャットボット管理 | US002 | 管理者 | チャットボットにアクセスできるユーザーの管理 | データ漏洩防止のため、権限を持つユーザーのみがチャットボットにアクセスできるようにする。 | Must | 1 | 2 |  | 500 |  | 0.83333 | 5 | 2.5 | 8.3333 |  | CT | 4000 | 4
3 | チャットボット管理 | US003 | 管理者 | ドキュメントのデータをベクターストアへ継続的に同期するプロセスの設定 | AIツールが常に最新で正確なドキュメントに基づいてユーザーの質問に回答し、情報の陳腐化を防ぐことを保証する。 | Must | 1 | 3 |  | 750 |  | 1.25 | 7.5 | 3.75 | 12.5
4 | チャットボット管理 | US004 | 管理者 | GitLabのデータをベクターストアへ継続的に同期するプロセスの設定 | 常に最新のデータに基づいて回答できる。 | Must | 2 | 3 |  | 750 |  | 1.25 | 7.5 | 3.75 | 12.5
5 | チャットボット管理 | US005 | 管理者 | Backlogのデータをベクターストアへ継続的に同期するプロセスの設定 | 常に最新のデータに基づいて回答できる。 | Must | 1 | 2 |  | 500 |  | 0.83333 | 5 | 2.5 | 8.3333
6 | チャットボット管理 | US006 | 管理者 | Slackのデータをベクターストアへ継続的に同期するプロセスの設定 | 常に最新のデータに基づいて回答できる。 | Must | 1 | 2 |  | 500 |  | 0.83333 | 5 | 2.5 | 8.3333
7 | チャットボット管理 | US007 | 管理者 | 運用要件に応じたエージェント（例：Code Agent）の有効化・無効化 | システムがユーザーに提供する機能を柔軟に制御できる。 | Should | 2 | 1.5 |  | 375 |  | 0.625 | 3.75 | 1.875 | 6.25
8 | チャットボット管理 | US008 | 管理者 | システムのパフォーマンスとコストの監視 | リソース使用を最適化し、運用予算を管理できる。 | Should | 3 | 1.5 |  | 375 |  | 0.625 | 3.75 | 1.875 | 6.25
9 | チャットボットの挙動 | US009 | プロジェクトマネージャー | プロジェクトのGitLabリポジトリに記録されたセキュリティ問題の集約 | 最も重要なリスクに対処するために、優先順位付けとリソース配分を行える。 | Could | 3 | 3 |  | 750 |  | 1.25 | 7.5 | 3.75 | 12.5
10 | チャットボットの挙動 | US010 | プロジェクトマネージャー | 優先度が高いが、～日以上遅延しているBacklog項目の特定 | ボトルネックを解消し、進捗を確保するためにタイムリーな介入を行える。 | Should | 3 | 1 |  | 250 |  | 0.41667 | 2.5 | 1.25 | 4.1667
11 | チャットボットの挙動 | US011 | プロジェクトマネージャー | BacklogのパフォーマンスデータとSlackの決定事項に基づいた週次レポートの自動生成 | 手作業でのデータ集計に時間を費やす代わりに、進捗の迅速な評価、ボトルネックや重要な決定の特定を行い、戦略的な意思決定に集中できる。 | Must | 2 | 2 |  | 500 |  | 0.83333 | 5 | 2.5 | 8.3333
12 | チャットボットの挙動 | US012 | プロジェクトマネージャー | オープン中のバグ総数に関する即時レポートの受信 | チームの品質状況や作業の滞り具合を迅速に把握できる。 | Could | 2 | 1.5 |  | 375 |  | 0.625 | 3.75 | 1.875 | 6.25
13 | チャットボットの挙動 | US013 | 開発者 | GitLabから同期された特定の関数またはコードファイルの動作ロジックの説明を要求 | システムの業務ロジックやアーキテクチャをより深く理解できる。 | Must | 2 | 2 |  | 500 |  | 0.83333 | 5 | 2.5 | 8.3333
14 | チャットボットの挙動 | US014 | 開発者 | 過去に開発された機能に関連する特定コードスニペットの検索 | コミット履歴やファイルを閲覧することなく、迅速にコードを再利用または参照できる。 | Should | 3 | 2 |  | 500 |  | 0.83333 | 5 | 2.5 | 8.3333
15 | チャットボットの挙動 | US015 | 開発者 | 多くの変更を含むマージリクエストの内容の要約 | 変更されたコードを一行ずつ読まなくても、MRの目的と範囲を迅速に理解できる。 | Could | 3 | 1 |  | 250 |  | 0.41667 | 2.5 | 1.25 | 4.1667
16 | チャットボットの挙動 | US016 | 開発者 | 特定のマージリクエストに対するコードレビューの要求 | 上司に正式なレビューを依頼する前に、自動的かつ迅速にフィードバックと改善提案を受けられる。 | Could | 3 | 1.5 |  | 375 |  | 0.625 | 3.75 | 1.875 | 6.25
17 | チャットボットの挙動 | US017 | ユーザー | IDを提供してBacklog内の特定のタスクまたは課題の詳細な説明を質問 | Backlogに直接アクセスすることなく、作業要件や問題の背景を明確に理解できる。 | Must | 2 | 2 |  | 500 |  | 0.83333 | 5 | 2.5 | 8.3333
18 | チャットボットの挙動 | US018 | ユーザー | Backlog課題の説明に記載されている用語や業務プロセスの説明を要求 | 技術的な作業の背後にあるビジネスの背景をより深く理解できる。 | Must | 2 | 2 |  | 500 |  | 0.83333 | 5 | 2.5 | 8.3333
19 | チャットボットの挙動 | US019 | ユーザー | Slackでの長いスレッドの要約を要求 | 各返信をすべて読まなくても、議論の最終的な結論を理解できる。 | Must | 3 | 1 |  | 250 |  | 0.41667 | 2.5 | 1.25 | 4.1667
20 | チャットボットの挙動 | US020 | ユーザー | 重要なドキュメントが更新された際、他のドキュメント（例：参照資料、関連プロセス）への影響評価 | レビュー・修正が必要なドキュメントを即座に特定し、ナレッジベース全体の一貫性を保ちつつ、情報の陳腐化を防ぐことができる。 | Must | 2 | 2 |  | 500 |  | 0.83333 | 5 | 2.5 | 8.3333
21 | チャットボットの挙動 | US021 | ユーザー | 数週間前にチャンネルで送信された「決済機能」に関する特定のメッセージを検索 | 何千ものメッセージをスクロールすることなく、過去の情報を迅速に検索できる。 | Should | 3 | 1 |  | 250 |  | 0.41667 | 2.5 | 1.25 | 4.1667
22 | チャットボットの挙動 | US022 | ユーザー | プロジェクトやデータ（進捗、品質、リスクなど）に関する一般的な質問 | 既存のすべてのドキュメント（Slack、Backlog、Gitlab、ドキュメント）に基づいて、正確な推論応答を受け取れる。 | Could | 3 | 2 |  | 500 |  | 0.83333 | 5 | 2.5 | 8.3333
23 | チャットボットの挙動 | US023 | ユーザー | ファイル（Word、Excel、PPT、PDF、画像）をアップロードして、そのデータに関する一般的な質問 | 自分で情報を読んだり、分析したり、抽出したりすることなく、アップロードされたファイルの内容に基づいてLLMが生成した正確で即時の回答を受け取れる。 | Must | 2 | 2.5 |  | 625 |  | 1.0417 | 6.25 | 3.125 | 10.4167
24 | チャットボットの挙動 | US024 | ユーザー | テキストでの説明や取得したデータ構造に基づいた構成図の描画 | テキストの説明を読むよりも、アーキテクチャ、ワークフロー、各コンポーネント間の関係を明確かつ理解しやすく視覚化できる。 | Could | 3 | 1.5 |  | 375 |  | 0.625 | 3.75 | 1.875 | 6.25
25 | チャットボットの挙動 | US025 | ユーザー | 最終決定を理解するため、クローズされた課題の最新コメントを要約 | やりとりの全スレッドを読まなくても、課題がクローズされた結果と理由を把握できる。 | Could | 3 | 1.5 |  | 375 |  | 0.625 | 3.75 | 1.875 | 6.25
26 | チャットボットの挙動 | US026 | ユーザー | ドキュメントに記載されている業務に関する任意の質問 | ドキュメント全体を検索・閲覧することなく、即座に正確な回答を受け取れる。 | Must | 1 | 3 |  | 750 |  | 1.25 | 7.5 | 3.75 | 12.5
27 | チャットボットの挙動 | US027 | ユーザー | チャットボットのウェブ検索 | 最新の情報を取得して回答する。 | Must | 1 | 2 |  | 500 |  | 0.83333 | 5 | 2.5 | 8.3333
28 | チャットボットの挙動 | US028 | ユーザー | チャットボットとのやり取り管理 | やり取りの履歴を閲覧できる。 | Must | 1 | 2 |  | 500 |  | 0.83333 | 5 | 2.5 | 8.3333
合計 | [9 empty] | 13875 |  | 23.125 | 138.75 | 69.375 | 231.25 | 11.5625

## ⑥想定スケジュール
⑦想定スケジュール
| # | Sprint | Sprint Goal | 工程 | 担当者 | 2025 | [7 empty] | 2026
[6 empty] | 11 |  |  |  | 12 |  |  |  | 01
[6 empty] | 07 | 14 | 21 | 28 | 05 | 12 | 19 | 26 | 02 | 09 | 16 | 23 | 30
マイルストーン
| 1 | Setup |  | プロジェクト準備/ 開発環境の構築 | SPLUS
| 2 |  |  | 仕様確認（スタディ） アプリケーション方式設計 | SPLUS
| 3 |  |  | 詳細設計 (プログラム設計・DB設計) | SPLUS
| 4 |  |  | Confirm 詳細設計 | 株式会社シーイーシー様
| 5 | Sprint01 4 Week | 最重要機能の開発 | コーディング〜単体テスト | SPLUS
| 6 |  |  | User Acceptance Test | 株式会社シーイーシー様
| 7 |  |  | 受入テスト対応 | SPLUS
| 8 | Sprint02 3 Week | 中優先度の機能開発 | コーディング〜単体テスト | SPLUS
| 9 |  |  | User Acceptance Test | 株式会社シーイーシー様
| 10 |  |  | 受入テスト対応 | SPLUS
| 11 | Sprint03 3 Week | 残りの機能開発 （低優先度） | コーディング〜単体テスト | SPLUS
| 12 |  |  | User Acceptance Test | 株式会社シーイーシー様
| 13 |  |  | リリース | SPLUS
▽11/01: プロジェクト開始
Setup
Sprint01
Sprint02
Sprint03

## Estimate (Revised) (hidden)
Common | [14 empty] | 生産性
Task ID | Task Name | OS | Size | Description |  |  |  |  | Output |  |  |  | Effort (day) |  |  |  | 2.4
1 | Preparation Phase | [11 empty] | 7 |  | CDD | 12000 | 12
1.1 | Environment Setup |  |  | Set up development environments for Java (OpenJDK 17/21) and C# (.NET 8/9), configure access to both evaluation tools |  |  |  |  | Functioning development environments, access to evaluation tools |  |  |  | 3
1.2 | Evaluation Methodology Design |  |  | Define detailed evaluation criteria, scoring systems, and standardized assessment templates |  |  |  |  | Evaluation methodology document, assessment templates |  |  |  | 4 |  | C-UT | 6000 | 6
2 | Verification Dataset Preparation | [11 empty] | 12 |  | CT | 6000 | 6
2.1 | Java Desktop Application Selection (Small) | Desktop | Small | Identify and select suitable small-scale Java desktop application from GitHub |  |  |  |  | Source code |  |  |  | 2
2.2 | Java Desktop Application Selection (Large) | Desktop | Large | Identify and select suitable large-scale Java desktop application from GitHub |  |  |  |  | Source code |  |  |  | 2
2.3 | Java Web Application Selection (Small) | Web | Small | Identify and select suitable small-scale Java web application with HTML/CSS frontend from GitHub |  |  |  |  | Source code |  |  |  | 2
2.4 | Java Web Application Selection (Large) | Web | Large | Identify and select suitable large-scale Java web application with HTML/CSS frontend from GitHub |  |  |  |  | Source code |  |  |  | 2
2.5 | C# WPF Desktop Application Selection (Small) | Desktop | Small | Identify and select suitable small-scale C# WPF desktop application from GitHub |  |  |  |  | Source code |  |  |  | 2
2.6 | C# WPF Desktop Application Selection (Large) | Desktop | Large | Identify and select suitable large-scale C# WPF desktop application from GitHub |  |  |  |  | Source code |  |  |  | 2
AIプログラミングツール (AI Programming Tool) Evaluation
Task ID | Task Name | Description | [6 empty] | Output |  |  |  | Effort (day)
3 | Task List Development | [11 empty] | 15
3.1 | Task Categories Definition | Define 10 major task categories (functionality additions, bug fixes, refactoring, etc.) | [6 empty] | List of major task categories with descriptions |  |  |  | 2
3.2 | Detailed Task Creation | Create 20 specific subcategory tasks for each major category (200 total tasks) | [6 empty] | Complete task list document with 200 specific tasks |  |  |  | 5
3.3 | Task Instructions Preparation | Prepare both coarse and specific instructions for each task | [6 empty] | Task instruction document with both instruction types |  |  |  | 8
Task ID | Task Name | OS | Size | Screen | LOC | File | Link | Description | Output | Testcase | Effort ( hour / Task ) | Capture Evident ( hour / Task ) | Effort (day)
4 | AI Programming Tool Execution and Evaluation | [11 empty] | 180
4.1 | Java Desktop Application | Desktop | Small | 13 | 3125 | 21 | https://github.com/sudhirkumar85/Hotel-Management-System/tree/master | Execute and evaluate tasks for small Java desktop applications with both AI models and instruction types | Evaluation data for Java desktop applications | 400 | 0.5 | 0.1 | 30
4.2 | Java Desktop Application | Desktop | Large | 24 | 6346 | 33 | https://github.com/kunaltyagi9/Travel-and-Toursim-Management-System.git | Execute and evaluate tasks for large Java desktop applications with both AI models and instruction types | Evaluation data for Java desktop applications | 400 | 0.5 | 0.1 | 30
4.3 | Java Web Application | Web | Small | 8 | 3462 | 85 | https://github.com/spring-projects/spring-petclinic.git | Execute and evaluate tasks for small Java web applications with both AI models and instruction types | Evaluation data for Java web applications | 400 | 0.5 | 0.1 | 30
4.4 | Java Web Application | Web | Large | 22 | 12800 | 339 | https://github.com/oburakcinar/Student-Management-System | Execute and evaluate tasks for large Java web applications with both AI models and instruction types | Evaluation data for Java web applications | 400 | 0.5 | 0.1 | 30
4.5 | C# WPF Desktop Application | Desktop | Small | 15 | 8512 | 161 | https://github.com/dattali18/WPF-.NET-Project | Execute and evaluate tasks for small C# WPF applications with both AI models and instruction types | Evaluation data for C# WPF applications | 400 | 0.5 | 0.1 | 30
4.6 | C# WPF Desktop Application | Desktop | Large | 16 | 29372 | 365 | https://drive.google.com/file/d/1eUXZ8xXpEfZE7TG-FTc9poIhRq2Gne0C/view | Execute and evaluate tasks for large C# WPF applications with both AI models and instruction types | Evaluation data for C# WPF applications | 400 | 0.5 | 0.1 | 30
Task ID | Task Name | Description | [6 empty] | Output |  |  |  | Effort (day)
5 | AI Programming Tool Analysis | [11 empty] | 4
5.1 | Data Compilation and Preprocessing | Compile evaluation data, prepare for analysis | [6 empty] | Preprocessed evaluation dataset |  |  |  | 2
5.3 | Findings Documentation | Document key findings, trends, and insights | [6 empty] | AI Programming Tool analysis report |  |  |  | 2
Total | [12 empty] | 218 | (day)
詳細設計/単体テスト作成ツール (Detailed Design/Unit Test Creation Tool) Evaluation
Task ID | Task Name | OS | Size | LOC | Description |  |  |  | Output |  |  |  | Effort (day)
6 | Design Document Evaluation | [11 empty] | 86.4
6.1 | Java Desktop Application | Desktop | Large | 6346 | Upload Java application source code, evaluate generated design documents and diagrams |  |  |  | Evaluation data for Java applications design documents |  |  |  | 10.5767
6.2 | Java Desktop Application | Web | Large | 16122 | Upload Java application source code, evaluate generated design documents and diagrams |  |  |  | Evaluation data for Java applications design documents |  |  |  | 26.87
6.3 | C# WPF Desktop Application | Desktop | Large | 29372 | Upload C# application source code, evaluate generated design documents and diagrams |  |  |  | Evaluation data for C# applications design documents |  |  |  | 48.9533
7 | Unit Test Evaluation | [11 empty] | 172.8
Task ID | Task Name | OS | Size | LOC | Description |  |  |  | Output |  |  |  | Effort (day)
7.1 | Java Applications Unit Test Evaluation | Desktop | Large | 6346 | Evaluate generated unit test patterns and code for Java applications, verify execution |  |  |  | Evaluation data for Java applications unit tests |  |  |  | 21.1533
7.2 | Java Applications Unit Test Evaluation | Web | Large | 16122 | Evaluate generated unit test patterns and code for Java applications, verify execution |  |  |  | Evaluation data for Java applications unit tests |  |  |  | 53.74
7.3 | C# Applications Unit Test Evaluation | Desktop | Large | 29372 | Evaluate generated unit test patterns and code for C# applications, verify execution |  |  |  | Evaluation data for C# applications design documents |  |  |  | 97.9067
Total | [12 empty] | 259.2 | (day)
477.2

## ⑦体制
⑥体制
プロジェクト推進の体制は以下を想定しております。
体制図
日本法人(契約窓口)
Ozawa
PMO(PMの上位管理者)
|  |  | Le Anh Duy | AnNT
PhuongND
プロジェクト管理
| 部長: 幸田様 |  | Project Manager (PM) |  | Comtor
|  |  | Nguyen Trieu Duong (DuongNT) |  | Tran Thi Phuong Thao (ThaoTTP)
日本語
（窓口：日本語の場合）
メンバー1
Nguyen Anh Kiet (KietNA)
メンバー2
Do Van Vinh (VinhDV)
メンバー3
Le Van Quy (QuyLV)
メンバー4
Do Trong Phu (PhuDT)
ラボ契約者
Splus-Software ラボチーム
Workthy様

## ⑧提供が必要なリソース
# | Resource Name | 説明
1 | AWS Account | AWSアカウントはプロジェクトで使用されます。 開発チームがサービスを作成・管理できるように、必要な権限のIAMユーザーまたはIAMロールを作ってください。
2 | Amazon Bedrock
3 | Amazon OpenSearch Service
4 | AWS Lambda
5 | Amazon S3
6 | Amazon API Gateway
7 | Amazon DynamoDB | コンバセーションを保存します。
8 | Amazon EventBridge | 指定されたリソースからデータを取得するスケジュールを作成します。
9 | Amazon CloudWatch | 監視し、ログを記録します。
10 | AWS Amplify | フロントエンドを実装します。
11 | Amazon CloudFront
12 | Amazon Route53
13 | Infrastructure as Code (IaC): - AWS CloudFormation - Hoặc Terraform | AWSにリソースを展開するためのインフラである。
14 | CI/CD: - CodePipeline - CodeBuild - CodeDeploy
15 | Amazon RDS (optional) - Postgres instance | ユーザーのデータ（設定など）を保存します。
16 | Amazon VPC | 以下を含むVPC（チャットボットのリソース用に分離されたプライベートなネットワーク環境）を作成します。 - 2つのプライベートサブネットを、各アベイラビリティゾーン（AZ）に配置
Option 1: IAM User - Developer/DevOps role (Using AWS managed policy )
# | Group | AWS Managed Policy
1 | Compute / API | - AWSLambda_FullAccess - AmazonAPIGatewayAdministrator
1 | Data layer | - AmazonS3FullAccess - AmazonDynamoDBFullAccess - AmazonRDSFullAccess - AmazonOpenSearchServiceFullAccess
1 | AI / ML | - AmazonBedrockFullAccess
1 | Monitoring & Event | - CloudWatchFullAccess - AmazonEventBridgeFullAccess
1 | Network / CDN | - AmazonVPCFullAccess - AmazonRoute53FullAccess - CloudFrontFullAccess
1 | App Hosting | - AmplifyFullAccess
1 | IaC | - AWSCloudFormationFullAccess - IAMPassRole
1 | CI/CD | - AWSCodeBuildAdminAccess - AWSCodeDeployFullAccess - AWSCodePipelineFullAccess
1 | Base IAM View | - IAMReadOnlyAccess - AWSSecurityAudit
Option 2: IAM User - Developer/DevOps role (custom least privilege policy)
# | Group | AWS Managed Policy
1 | Compute / API | Action: - lambda:CreateFunction - lambda:UpdateFunctionCode - lambda:UpdateFunctionConfiguration - lambda:GetFunction - lambda:InvokeFunction - lambda:DeleteFunction - apigateway:POST - apigateway:PUT - apigateway:GET - apigateway:DELETE - apigateway:PATCH Resource: - arn:aws:lambda:<REGION>:<ACCOUNT_ID>:function/<YOUR_APP_PREFIX>* - arn:aws:apigateway:<REGION>::/restapis/<API_ID>/*
1 | Data layer | Action: - s3:ListBucket - s3:GetObject - s3:PutObject - s3:DeleteObject - dynamodb:GetItem - dynamodb:PutItem - dynamodb:UpdateItem - dynamodb:DeleteItem - dynamodb:Query - dynamodb:Scan - rds:DescribeDBInstances - rds:ModifyDBInstance - rds:RebootDBInstance - opensearch:CreateDomain - opensearch:DescribeDomain - opensearch:DeleteDomain Resource: - arn:aws:s3:::<YOUR_BUCKET_PREFIX>* - arn:aws:s3:::<YOUR_BUCKET_PREFIX>*/* - arn:aws:dynamodb:<REGION>:<ACCOUNT_ID>:table/<YOUR_TABLE_PREFIX>* - arn:aws:rds:<REGION>:<ACCOUNT_ID>:db:<YOUR_DB_INSTANCE_PREFIX>* - arn:aws:es:<REGION>:<ACCOUNT_ID>:domain/<YOUR_OS_DOMAIN_PREFIX>* - arn:aws:opensearch:<REGION>:<ACCOUNT_ID>:domain/<YOUR_OS_DOMAIN_PREFIX>*
1 | AI / ML | Action: - bedrock:InvokeModel - bedrock:ListModels - bedrock:DescribeModel - bedrock:CreateModel - bedrock:DeleteModel Resource: "*"
1 | Monitoring & Event | Action: - logs:CreateLogGroup - logs:CreateLogStream - logs:PutLogEvents - cloudwatch:PutMetricData - cloudwatch:DescribeAlarms - cloudwatch:PutAlarmState - events:PutRule - events:PutTargets - events:ListRules - events:DescribeRule Resource: "*"
1 | Network / CDN | Action: - ec2:DescribeVpcs - ec2:CreateVpc - ec2:DeleteVpc - ec2:ModifyVpcAttribute - route53:ListHostedZones - route53:ChangeResourceRecordSets - cloudfront:CreateDistribution - cloudfront:UpdateDistribution - cloudfront:DeleteDistribution Resource: "*"
1 | App Hosting | Action: - amplify:CreateApp - amplify:DeleteApp - amplify:UpdateApp - amplify:GetApp - amplify:StartDeployment - amplify:StopJob Resource: - arn:aws:amplify:<REGION>:<ACCOUNT_ID>:apps/<YOUR_APP_PREFIX>*
1 | IaC | Action: - cloudformation:CreateStack - cloudformation:UpdateStack - cloudformation:DeleteStack - cloudformation:DescribeStacks - iam:PassRole Resource: - arn:aws:cloudformation:<REGION>:<ACCOUNT_ID>:stack/<YOUR_STACK_PREFIX>* - arn:aws:iam::<ACCOUNT_ID>:role/<YOUR_CF_EXECUTION_ROLE>
1 | CI/CD | Action: - codepipeline:StartPipelineExecution - codepipeline:GetPipeline - codepipeline:ListPipelines - codebuild:StartBuild - codebuild:BatchGetBuilds - codedeploy:CreateDeployment - codedeploy:GetDeployment Resource: "*"
1 | Base IAM View | * PassRole_Restricted Action: - iam:PassRole Resource: - arn:aws:iam::<ACCOUNT_ID>:role/<LAMBDA_EXECUTION_ROLE> - arn:aws:iam::<ACCOUNT_ID>:role/<CODEBUILD_SERVICE_ROLE> - arn:aws:iam::<ACCOUNT_ID>:role/<CODEDEPLOY_SERVICE_ROLE> * Base_IAM_ReadOnly Action: - iam:GetUser - iam:ListAttachedUserPolicies - iam:ListGroupsForUser - sts:GetCallerIdentity Resource: - arn:aws:iam::<ACCOUNT_ID>:user/${aws:username}